Meeting Minutes — Group B, Development Team Project

Module: Machine Learning (ML_PCOM7E) — MSc Data Science / MSc AI

Assignment: Development Team Project — Airbnb Business Analysis (Track 2: Deep Learning)

Meeting: Project status meeting #2

Date & time: Tuesday, 12 May 2026

Platform: Microsoft Teams (recorded; transcript and recording uploaded to the shared Google Drive)

Attendance

| Name | Role | Status |
| --- | --- | --- |
| Richárd Szépi | Coordinator & Report Editor | Present |
| Maha Hegde | Data & Modelling Lead | Present |
| Mohammed Lari | Research & Critical Analysis Lead | Present |
| Abdullah | — | Absent |
| [Team member 5] | — | Absent (no contact established) |
| [Team member 6] | — | Absent (no contact established) |

Mohammed will attempt to reach the three absent members by email this week. If contact still cannot be established, the tutor (Dr. Elizabeth Oladapo) will be informed so that she is aware of the situation.

Agenda

- Agree on the business question

- Define and assign project roles

- Agree on next steps and the working timeline

Discussion and decisions

1. Business question

Maha had reviewed the assignment brief against Track 2's stated focus areas (image-based analysis, text-based sentiment classification, demand forecasting) and the AB_NYC_2019.csv dataset. He flagged that the dataset contains no listing images and no review text — only aggregate review counts — which constrains the conventional Track 2 approaches. The only sentiment-style avenue available would be analysing the name field (listing titles), e.g. whether positively-worded titles ("clean", "charming", "affordable") correlate with higher prices.

Richárd presented an alternative framing developed during prior preparation: a comparative price-prediction study using a neural network against a classical regression baseline, with interpretation of which features drive the neural network's predictions.

The team discussed both options and agreed that the price-prediction comparison:

- Satisfies the Track 2 requirement for deep learning (neural network on tabular data).

- Is fully feasible with the data available, with no scraping or external sources required.

- Provides a natural comparative narrative for the report and for the cross-track group discussion forum.

- Is appropriately scoped for the 1,000-word report.

Decision: The agreed business question for the project is: "Can a neural network predict NYC Airbnb listing prices more accurately than classical regression, and which listing features drive its predictions?"

The team noted that, per the tutor's clarification, the focus is the analytical report and discussion of approach and findings — not a complete standalone system or production code. Basic artefacts, screenshots, and visualisations will be produced and stored in the e-portfolio working folder for Unit 12.

2. Project roles

The team agreed on a three-role structure rather than splitting data and modelling, since these tasks are tightly coupled for this question.

| Role | Owner | Primary responsibilities |
| --- | --- | --- |
| Coordinator & Report Editor | Richárd | Meeting facilitation, agendas, minutes, shared report scaffolding, integration of contributions, word-count management, final editing, Turnitin check, submission |
| Data & Modelling Lead | Maha | EDA, data cleaning and preparation, feature engineering, baseline regression, neural network implementation, evaluation, visualisations, drafting methodology and results sections |
| Research & Critical Analysis Lead | Mohammed | Literature review, business framing, criticality, drafting introduction and discussion sections, contribution to the cross-track comparative reflection |

Should Abdullah or the other absent members join later, additional responsibilities can be assigned at that point.

3. Working timeline and ways of working

- The team agreed on a self-imposed internal deadline one week ahead of the official deadline: targeting a complete, integrated draft by 1 June 2026, with the final week used for review, refinement, Turnitin, and submission ahead of the official deadline of Monday 8 June 2026, 23:55.

- Next meeting is next week, same time. Richárd will issue the calendar invite.

- All shared artefacts (transcript, recording, dataset copy, references, draft report, visualisations) will be stored in the Google Drive shared folder Maha set up.

- A copy of the Kaggle AB_NYC_2019.csv dataset will be saved to the shared Drive for reference.

Action items

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| 1 | Send meeting minutes and recording link to the team channel | Richárd | 13 May 2026 |
| 2 | Issue calendar invite for the standing weekly Monday meeting (19 May, same time) | Richárd | 13 May 2026 |
| 3 | Reach out to the three absent team members by email; escalate to tutor if no response | Mohammed | By 18 May 2026 |
| 4 | Save a reference copy of the Kaggle dataset (AB_NYC_2019.csv) to the shared Drive | Richárd | By 18 May 2026 |
| 5 | Create the shared report document (sections, headings, word-count budgets, named owners) | Richárd | By 18 May 2026 |
| 6 | Circulate a high-level working plan per role | Richárd | By 18 May 2026 |
| 7 | Begin EDA on the dataset, draft initial visualisations, sketch modelling approach | Maha | By 19 May 2026 |
| 8 | Begin literature search and gather useful references for framing and criticality | Mohammed | By 19 May 2026 |
| 9 | Support the literature search in parallel | Richárd | By 19 May 2026 |

High-level working plan per role

The plan below covers the four weeks from this meeting to submission. It is intentionally high-level and will be refined at each Monday meeting.

| Week | Coordinator & Report Editor (Richárd) | Data & Modelling Lead (Maha) | Research & Critical Analysis Lead (Mohammed) |
| --- | --- | --- | --- |
| Week 1 — 12 to 18 May Setup & scoping | Issue minutes and meeting invite. Set up shared report document with sections and word budgets. Save dataset to Drive. Draft this working plan. Support literature search. | Begin EDA on the dataset. Identify data quality issues, candidate features, and sketch modelling approach (baseline + neural network architecture, evaluation metrics). | Begin literature search: Airbnb pricing studies, neural networks for tabular data, feature interpretability. Aim for 5–8 useful references. |
| Week 2 — 19 to 25 May Build & first results | Monitor progress and integrate early drafts. Manage word count. Coordinate cross-section consistency. Draft introduction/conclusion framing. | Finalise cleaned dataset and feature set. Produce baseline regression and first neural network results. Prepare 2–3 visualisations for the report. Draft methodology and results sections. | Finalise literature review. Draft introduction (business context, rationale for deep learning) and discussion (criticality, interpretation, limitations). |
| Week 3 — 26 May to 31 May Integration & internal deadline | Integrate all sections into the master document. Full editorial pass: structure, flow, word count, Harvard referencing (Cite Them Right). Run Turnitin originality check. | Finalise model results and visualisations. Support interpretation and reviewer comments. Confirm captions and figure references. | Finalise discussion section. Draft the team's reflection for the cross-track comparison on the discussion forum. Review and comment on the full draft. |
| Week 4 — 1 to 8 June Review, polish, submit | Final review meeting with the team. Apply final edits. Confirm references and word count. Submit the report before 23:55 on 8 June. Complete individual peer evaluation. | Review the integrated document. Apply any final edits to results and figures. File personal artefacts in the e-portfolio working folder. Complete individual peer evaluation. | Post the team's reflection on the discussion forum. Review the integrated document. File personal artefacts in the e-portfolio working folder. Complete individual peer evaluation. |

Next meeting

Monday 19 May 2026, same time (Microsoft Teams). Standing agenda: progress on action items, EDA findings, literature update, scope confirmation, next-week assignments.