Meeting Minutes — Group B, Development Team Project

Module: Machine Learning (ML_PCOM7E) — MSc Data Science / MSc AI Assignment: Development Team Project — Airbnb Business Analysis (Track 2: Deep Learning) Meeting: Project status meeting #3 Date & time: Monday, 19 May 2026, 18:02 CEST (duration 8m 07s) Platform: Microsoft Teams (recorded; transcript uploaded to the shared Google Drive)

Attendance

| Name | Role | Status |
| --- | --- | --- |
| Richárd Szépi | Coordinator & Report Editor | Present |
| Maha Hegde | Data & Modelling Lead | Present |
| Mohammed Lari | Research & Critical Analysis Lead | Present |
| Abdullah | Research & Critical Analysis support | Absent (in contact via group chat; supporting Mohammed on research and critical analysis) |
| [Team member 5] | — | Absent (no response to outreach) |
| [Team member 6] | — | Absent (no response to outreach) |

Mohammed contacted the three absent members; only Abdullah responded and has agreed to contribute, supporting Mohammed on the research and critical analysis work. The other two members did not reply. The team will keep the tutor informed if they remain uncontactable.

Agenda

- Review progress against the previous meeting's action items

- Confirm tasks for the coming week

- Agree next steps and next meeting

Progress review — action items from meeting #2 (12 May)

| # | Action | Owner | Status |
| --- | --- | --- | --- |
| 1 | Send meeting minutes and recording link to the team channel | Richárd | Partially done — minutes sent; recording could not be uploaded (technical/upload issue). Team agreed minutes are sufficient. |
| 2 | Issue calendar invite for the standing weekly Monday meeting | Richárd | Done |
| 3 | Reach out to the three absent team members; escalate to tutor if no response | Mohammed | Done — outreach completed; only Abdullah responded. |
| 4 | Save a reference copy of the Kaggle dataset to the shared Drive | Richárd | Outstanding — carried forward. |
| 5 | Create the shared report document | Richárd | Pending (intentionally) — to be created once initial working materials (EDA draft + literature list) are available. |
| 6 | Circulate a high-level working plan per role | Richárd | Done — included in the minutes file. |
| 7 | Begin EDA, draft visualisations, sketch modelling approach | Maha | In progress — mostly complete but slightly delayed; will share at the next meeting. No support needed yet. |
| 8 | Begin literature search and gather references | Mohammed | In progress — initial set of references gathered; to be reviewed and uploaded to the shared Drive. To be split with Abdullah. |
| 9 | Support the literature search in parallel | Richárd | In progress — has made progress; will add references once Mohammed's list is uploaded. |

Overall: the project is broadly on track. The EDA is slightly delayed and will now be shared at the next meeting rather than mid-week; Maha is confident this will not affect the downstream timeline.

Discussion and decisions

1. EDA and modelling

Maha reported the EDA is mostly complete but slightly delayed. He will share the first draft at the next meeting (26 May) rather than mid-week. He does not need support at this stage but may request input once the draft is shared. The team confirmed this is acceptable.

2. Literature review

Mohammed has gathered an initial set of references and will review and upload them to the shared Drive. Abdullah will support Mohammed on the research and critical analysis work, and the two will split the literature between them; the team confirmed the relevant areas are covered. Richárd will add further references on top of Mohammed's list once uploaded.

3. Report compilation sequencing

The team agreed that once the initial literature list and the first EDA draft are available, Richárd will begin compiling the report and then run the technical/quality-assurance steps (integration, structure, word count, referencing, Turnitin). Mohammed is currently working on the first draft of the introduction and will aim to have his introduction and literature review ready for joint review at the next meeting.

4. Abdullah's contribution

Abdullah will support Mohammed on research and critical analysis. He has already been notified via the group chat and can progress his part in coordination with Mohammed.

5. Timeline reaffirmed

The team reaffirmed the plan to have a substantial amount of work compiled by the next meeting, giving Richárd roughly one week to assemble and finalise the full report ahead of submission, with a couple of days of buffer for final checks before the official deadline of Monday 8 June 2026, 23:55.

Action items

| # | Action | Owner | Due |
| --- | --- | --- | --- |
| 1 | Save a reference copy of the Kaggle dataset to the shared Drive (carried over) | Richárd | By 26 May 2026 |
| 2 | Review and upload the initial literature reference list to the shared Drive | Mohammed | This week |
| 3 | Add further literature references on top of Mohammed's list | Richárd | After list uploaded |
| 4 | Complete and share the first EDA draft (with initial visualisations) | Maha | By next meeting (26 May) |
| 5 | Finalise introduction and literature review, ready for joint review | Mohammed (with Abdullah's support) | By next meeting (26 May) |
| 6 | Create the shared report document and begin compilation once EDA + literature are in | Richárd | Once materials available |
| 7 | Send the calendar invite for the next meeting and upload these minutes to the shared folder | Richárd | 20 May 2026 |

Next meeting

Monday 26 May 2026, same time (Microsoft Teams). Planned agenda: joint review of compiled work to date — Maha's EDA results, Mohammed's introduction and literature review — and confirmation of remaining steps toward the internal deadline.